## Folha1
Days (Week 04 - 11 November)
Backlog ID | Estimated Duration | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Organization of Ideas | 4 | Days (Week 04 - 11 November) 3: 4; Days (Week 04 - 11 November) 4: 0; Days (Week 04 - 11 November) 5: 0; Days (Week 04 - 11 November) 6: 0
Study the Code | 25 |  | 2 | 5 | 5 | 8 | 5
New Functionalities | 14 | Days (Week 04 - 11 November) 3: 3; Days (Week 04 - 11 November) 4: 2; Days (Week 04 - 11 November) 5: 4; Days (Week 04 - 11 November) 6: 5
User Story | 10 | Days (Week 04 - 11 November) 3: 2; Days (Week 04 - 11 November) 4: 2; Days (Week 04 - 11 November) 5: 2; Days (Week 04 - 11 November) 6: 4
Report | 4 | Days (Week 04 - 11 November) 3: 0; Days (Week 04 - 11 November) 4: 0; Days (Week 04 - 11 November) 5: 0; Days (Week 04 - 11 November) 6: 4
Idealized burn | 57 | 47.5 | 38 | 28.5 | 19 | 9.5 | 0 | 0 | 0
Actual Burndown | 57 | 57 | 55 | 41 | 32 | 18 | 0 | 0 | 0